PROVIDENCE HOUSING AUTHORITY

FACILITIES MANAGEMENT

Board of Commissioners subcommittee meeting

Capital Improvements

January 28, 2020

Major Projects Underway

- The Dexter Manor elevator modernization project is set to begin on January 25, 2021.  As with other elevator modernizations one elevator car will be taken out of service at a time.  An expected completion date for this is in Fall of 2021.

- The Kilmartin Plaza elevator modernization has surpassed the halfway mark.  The first car has been completed and work on the second car has begun.

- The Dominica Boiler replacement project sponsored by RISE has been completed and is fully functional.

- Chad Brown roofing project is about 50% complete.

- The CDBG funded server project that PHA and Providence City Council are collaborating on is preparing to move past the legal phase into the RFP phase.

- Deck and ramp replacements at Scattered Sites are nearing completion with just the final two buildings remaining.

- The Dominica sprinkler project is mechanically complete.  Finishing touches with the Fire Alarm Systems are underway.

- Further information is available in the monthly management report

- Roof replacement at 335 is near completion.  The Hi-rise roof has been replaced.  We are currently waiting for materials to arrive to complete the lower roof overhang in front of the lobby at 335.

- Sprinkler Systems at Carroll Tower, Parenti Villa, and Dexter Manor are now in the beginning stages of work.  As of right now only work in common areas is happening.

- Exterior renovation projects at Hartford Park and Scattered Sites is expected to be completed by November 30, 2020. About 98% finished.

- Further information will be provided in the Monthly Management Report.

- The Authority has applied for CDBG money with the COP to replace the sliding doors at Dexter, Parenti and Kilmartin; CFP funds will be needed to supplement the project.

- The fire alarm/sprinkler installation project at 335 Hartford is approximately 98% complete; this project has resumed and is expected to be completed within 2 months.

- The Lead Consultant has reviewed all the lead test results and is currently creating the scope of work. This project will be funded through a $975,000 lead grant awarded by HUD for Hartford, Chad/Ad/Sun and Manton; CFP funds will also be used for this project.

- A contract has been signed to install panic bar hardware on all common stairwell doors at Dexter I and II; funding will be CDBG from the City of Prov. and CFP funds.

- A vendor has been selected for a professional design for emergency generator transfer switch and emergency generator interface system at the Tavares Center at Chad Brown and the community room at 144 Dodge St.

- A low bidder has been identified for elevator modernization at 335 Hartford; a contract has been signed.

- A bid package is currently advertised to install the new outside patio seating are at 50 Laurel Hill.